## Slide 1: Salient Features of the model document dated 20th November 2018 and further amended on 28th November 2018

## Slide 2
  Schedules :-
    There were 16 Schedules from A to P
    Now 18 Schedules- Q& R added
a) Q is for Tests on Completion of Maintenance Period
b) R is for Taking over Certificate
    In Schedule A to P :
a) Total amendments are 31 Nos.
b) Total additions are 5 Nos.
c) Total changes are 36 Nos.
Sl. No | Document | Amendment | Addition | Total Change
1 | DCA | 92 | 52 | 144
2 | RFP | 41 | 13 | 54
3 | SCHEDULE | 31 | 5 | 36
General statistics

## Slide 3
  RFP :-
    Total changes – 54
    In 6 chapters :-
a) Amendments – 35
b) Addition – 8
    In appendices & Annexure :-
a) Amendments – 6
b) Addition – 5
  DCA :-
    27 Articles – No addition in Articles.
      (a) Total amendments – 92
    (b) Total New addition – 52
    Total Changes – 144
    Article 14- Payment has maximum of 17 amendments.

## Slide 4
  The new document has ceased all speculative tendering in forms of cost and time.
  Contractor has to consider the contract holistically in the surrounding environment and the cause. He will be sole responsible for all coordination among sub contractors and other contractors for timely delivery.
  The Authority is responsible to provide 90% of land including 5 Km of continuous length in 30 days including LA, FC, and EC for balance land it has to categorically mention the time and date in Schedule ‘A’. The 90% land should be in possession with Authority before issue of LOA.
  Environment clearance to be obtained by the Authority before LoA.
  If appointed date is not given in 90 days the contract is to be terminated at the settlement of 1% in favour of contractor for roads and 3% for Standalone Bridge.
  Once appointed date is given, contractor is bound to deliver in stipulated time without any time and cost over run on the plea of Site, hydrological, climate, sub surface condition etc.
  The delay will accrue max 1% of damage to the Authority.
Gist's of amendments and changes in model EPC documents (1/2)

## Slide 5: Gist's of amendments and changes in model EPC documents (2/2)
  8. There is no provisional completion and it has to be completed in all respect.
  9. Additional warranties against the following are being obtained from the contractor–
    intellectual property rights in new clause 5.1 (ii).
    The work done has warranty by the contractor in the DLP against not meeting Authority’s requirement – Clause 5.1 (iv)
    Warranty by the contractor to translate the technology to the Authority without any defect 5.1 (v) and (vi)
    Warranty against past criminal records and non performance.
    10. Clearance of site after work to be done in all respect.
    11. The scope of utility shifting be part of schedule ‘B’ (amended in clause 9.2) and for delay no claim against Authority.

## Slide 6
Major Amendments in DCA

## Slide 7
  PERFORMANCE BANK GUARANTEE submission dates extended to 30 days from 10 days.
  PERFORMANCE BANK GUARANTEE & Additional PERFORMANCE BANK GUARANTEE shall be valid 60 days beyond DLP against 60 days in case of PERFORMANCE BANK GUARANTEE & 28 days after completion for ADDITIONAL PERFORMANCE BANK GUARANTEE.
  New option for 50% of PERFORMANCE BANK GUARANTEE & ADDITIONAL PERFORMANCE BANK GUARANTEE within 30 days of LOA and balance within 30 days of signing of agreement.
  Extension of 60 days for submission with penalty @ 0.01% even for part PERFORMANCE BANK GUARANTEE & ADDITIONAL PERFORMANCE BANK GUARANTEE against the earlier 30 days.
  New clause to appropriate the bid security if PERFORMANCE BANK GUARANTEE & ADDITIONAL PERFORMANCE BANK GUARANTEE not submitted in 60 days of extended time.
  Payment of yearly interest @ 9% for delay in return of PERFORMANCE BANK GUARANTEE & ADDITIONAL PERFORMANCE BANK GUARANTEE.
Performance Bank Guarantee & Additional Performance Bank Guarantee (Article-7)

## Slide 8
  Joint Memorandum in 10 days against earlier 30 days and shall be termed as Handover memorandum (HM).
  Before appointed date, Authority should have possession of at least 90% of total project length and relaxation on this account cannot be done by any party (New clause 8.2V)
  Appendix ‘A’ should not indicate cumulative length of more than 10% in any case for handing over after appointed date.
  A monthly land possession report till expiry of 180 days from appointed date for balance 10% land. If ROW (balance 10%) given in time, there will be no extension of time granted.
  If not given Authority can withdraw this work and if provided before scheduled completion, the contractor can take up this work without any additional cost.
Signing of Contract (Article-8)

## Slide 9: Utility Sifting (Article-9)
  Utility Sifting
  The scope of utility shifting be part of schedule ‘B’ (amended in clause 9.2) and for delay no claim against Authority.
  Earlier beyond 180 days the contractor was getting damages as applicable for ROW.
Dismantling of Structures (new clause 9.5)
  Contractor is responsible the dismantling and disposing in accordance with applicable law. In case of reasons beyond control of the contractor damages as applicable for ROW and time extension.

## Slide 10
AE to be appointed before appointed date earlier within 30 days after appointed date.
  Freedom to contractor to start the work with AE’s approval (beyond 15 days) withdrawn. It’s contractor’s responsibility to get approval of AE within 90 days (New clause 10.2(iv)h)
  If damages due to delay exceed 10% of the contract price an account of Contractor’s default, Authority is entitled to terminate the Contract considering no cure.
  If contractor fails to complete the work more than Rs 300 Cr. within 90 days of PDC, the Contractor shall be deemed not eligible for future projects.
  Maintenance to be carried out at the level of condition at appointed date not 10 days prior to the agreement.
  Time extension to be communicated within 30 days instead of earlier 60 days by AE.
    Two additional clause (10.8 & 10.9)
  A built record maintenance by Contractor at side
  Intellectual property of Authority
Design and construction of the Project highway (Article-10)

## Slide 11
  Requirement in MPR has been now specified which includes 19 explicits reports as part of MPR earlier there was no such
  Authority Engineer has to carry out 50% check against earlier 20%
  Requirement of staff & labour elaborated vide the new clauses 11.18 giving 7 specific requirements.
Quality Assurance, Monitoring & Supervision (Article-11)

## Slide 12: Completion certificate (Article-12)
  Provisional certificate completely deleted
  Others minor changes

## Slide 13
  Earlier Authority can propose the change before completion certificate now within 6 months of AD only.
  The COS (other than major structure) to be executed before completion of 50% of the scheduled completion of work and without any claims i.e. EOT etc.
  Clauses 13.1.3 deleted (Change of Scope proposed by contractor to reduce Cost & accelerate the work.
  If Authority determine the COS Authority Engineer has to respond within 15 days earlier there was no limit prescribed.
  Contractor can propose within 90 days of AD (new clause 13.2 (ii)
  COS to be calculated on SOR, MoRTH etc and to be lowered proportionately if contract cost is less than estimated cost with following conditions.
  If difference between costing of Authority Engineer & Contractor is 10% cost of AE be binding
  Design changes @1% for works difference from original scope
  Decision of COS to be intimated within 15 days
  If contractor does not agree for COS proposed by Authority, work can be executed by other Contractor
Change of scope (Article-13)

## Slide 14
  Maintenance
  Separate maintenance period of 5 years @.25, 0.25, 0.5, 0.5 & 1 for flexible and 10 years for rigid @ .25 x3, 0.5x4 & 0.75x3 against the earlier clauses of 90% on completion
  For standalone @ 025x5 & 0.5x5
  After completion of maintenance period taking over certificate to be issued (New clause 14.10)
There is no major change in Article 15 & 16. However ROBOTS are permitted for diversion & control of traffic during construction.
Defect liability
  5 years for flexible
  10 years for Rigid, Standalone structures, stretches with new technologies.
Maintenance (Article-14) & Defect liability Period (Article-17)

## Slide 15: Authority Engineer (Article-18)
In unavoidable circumstances, Authority may appoint an officer as Authority Engineer.
Officer in change has been made responsible for overall supervision and Authority Engineer is to assist officer.

## Slide 16
  Earlier contract price was inclusive of maintenance now changes.
  Advance payment of 10% intact but interest increase by 3% over Bank rate.
  Additional 5% for equipment intact.
  Part Mobilization Advance @ min 2.75% is admissible
  Deduction @ 15% of each SPS but to be repaid before the time of scheduled 80% completion.
  If cumulative SPS cost < 20% within time of scheduled 50% completion than BG of Mobilization Advance to be encashed.
  If Contract terminated than interest of Mobilization Advance shall be bank rate+5%
  For maintenance also a MPR i.e. monthly maintenance statement to be submitted and paid.
  Delay in payment the interest rate increased to 9% against earlier 2% + Bank Base Rate.
  Price indices have now been redefined. Price variation is now applicable to maintenance also
  Bonus remained at max 5% only.
Payments (Article – 19)

## Slide 17
  General requirements of Insurance polices have now been specified with 10 defined compliances which was earlier not there.
Insurance (Article-20)

## Slide 18: Termination (Article-23)
  This has been strengthen by adding 5 clause for intellectual property, bribery etc.
  Bribery, gift, gratuity, commission to any person other than contractor’s personnel is added in default list for termination
  Addition of new clause (23.9) foreclosure with mutual consent.

## Slide 19: Dispute resolution (Article-26)
  If dispute through conciliator not settled than before approaching arbitrator the conciliation to be explored through conciliation committees of Independent experts set by authority.
  No arbitration involving claim upto Rs. 50 lakhs
  50 lakhs to 50 Crores through sole arbitrator
  More than 50 Crore Arbitral Tribunal comprising of 3 arbitrators.

## Slide 20
Major Amendments in RFP

## Slide 21: Introduction (Section-1)
DPR shall be part of RFP as earlier
1.1.2 & 1.1.3, 1.23 & 2.1.3 and 2.1.6, 2.1.7 with 1.2.4 merged

## Slide 22: Instruction to bidders (Section-2)
Condition for more than 50% stake by outsider remained same i.e. subject to approval of competent Authority. If this situation arises after LOA and L1 denied security clearance than L-2 & L-3 can be offered.
The clause 2.1.18 vide which if bidder is barred the MoRTH is not eligible for bidding has been deleted and
Vide clauses 2.1.14 (iii) word ‘non performer’ used and definition of non performer given with 13 explicit parameters including termination
JV for more than Rs.100 Cr. intact
Bid capacity updated Bonus in last 5 years shall be added.

## Slide 23: Instruction to bidders (Section-2)
Highway sector redefined as highways, expressways, bridges, tunnel and airfield by deleting Railways, Metro rails & ports and added in core sector
Performance Bank Guarantee to be submitted within 30 days against the earlier 10 days.
Three new annexure added
  one declaring no investigation pending against bidder in India or outside India
  Second for amount of bonus received in last 5 years.
  Third stating that Contractor has not failed to complete the work beyond 90 days of scheduled PDC of work costing more than Rs.300 Cr.

## Slide 24
Major Amendments in Schedules

## Slide 25: Amendment in Schedules
No major changes in A to G (G has been modified as per DCA)
Format of Schedule ‘B’ reframed
Minor changes in Schedule ‘H’
Schedule ‘H’ - Earthwork of shoulder
Schedule ‘K’ i.e. tests on completion has now been elaborate and following 5 test vide clause 5 made mandatory
  Surface defects of pavement by Network Survey Vehicle (NSU)
  Roughness of pavement by NSU
  Strength of pavement by falling weight detectometer
  Test of bridges by Mobile Bridge Inspection Unit (MBU)
  Road signs test by Retro – reflectometer
NSU to be done before issue of completion certificate
In schedule ‘P’, insurance of 15% of Contract price to be maintained between CC and DLP in addition to other applicable insurance as per Law.
Addition of schedule ‘Q’ for Tests on completion of maintenance period for Riding quality test (2200 mm / Km) and visual & physical test.
Additions of Schedule ‘R’ format for taking over certificate is enclosed now.

## Slide 26: Errors in the Model documents
Error in DCA
Clauses 23.5.2 Authority Engineer to intimate valuation of unpaid works in 30 days whereas by 23.5.1, Authority Engineer has been directed to proceed within 45 days for such valuation. The contradiction to be reconsidered by making provision in 23.5.1 as 15 days or in 23.5.2 as 60 days

## Slide 27
Thank You