## Total Cost
Sl. No. | Components | Amount
1 | Road works (both External Connectivity and Internal Roads) including culverts, Minor bridges, underpasses, overpasses, approaches to ROB/RUB/ Structures, Major bridge (length > 60m) works and RoB / RUB / Elevated sections / Flyovers including viaducts, if any, Drainage & other works at External Roads (but excluding service roads) | 1305008307.8544
5 | Internal Infrastructure Works, i.e. Potable Water Supply System including Intake Works, Recycled Water Supply System, Sewerage System | 195526979.91
6 | Internal Power Supply System including Street Lighting, Data & Telecommunication | 46885338.4227
| Sub-Total | 1547420626.1871
| Provision towards Works Contract GST @ 12 % | 185690475.1425
| Grand Total | 1733111101

## Contract Price Weightages (hidden)
ITEM | WEIGHTAGE IN PERCENTAGE TO THE CONTRACT PRICE | STAGE FOR PAYMENT | PERCENTAGE WEIGHTAGE | TOTAL CONTRACT PRICE
1 | 2 | 3 | 4 | 2
Road works including culverts (but excluding service roads) | 51.09% | A-Widening and Strengthening of existing road |  | 489664227
|  | (1) Earthwork up to top of the sub-grade including excavation in soil, soft rock and hard rock, removal of unserviceable soil etc | 3.09%
|  | (2) Sub Base courses | 3.91%
|  | (3) Non Bituminous Base Course | 2.2%
|  | (4) Bituminous Base Course | 4.34%
|  | (5) Wearing coat | 2.5%
|  | (6) Widening and repair of culverts | 0%
B 1- New six/ four lane alignment / bypass (Flexible pavement)
|  | (1) Earthwork up to top of the sub-grade | 5.34% |  | 143822134
|  | (2) Sub Base Course | 6.43% |  | 126643000
|  | (3) Non Bituminous Base Course | 5.62%
|  | (4) Bituminous Base Course | 8.38%
|  | (5) Wearing coat | 6.34%
B 2- Reconstruction / New lane alignment / bypass (Rigid pavement)
|  | (1) Earthwork and sub-grade preparation | 12.01% |  | 143822134
|  | (2) Sub Base and Base Course | 8.33% |  | 126643000
|  | (3) Pavement Courses (DLC and PQC) | 12.15%
|  | (4) Pavement Quality Control (PQC) course | 0%
C 1- Reconstruction / New Service road/ Slip Road (Flexible pavement)
|  | (1) Earthwork up to top of the sub-grade | 0%
|  | (2) Sub Base Course | 0%
|  | (3) Non Bituminous Base Course | 0%
|  | (4) Bituminous Base Course | 0%
|  | (5) Wearing coat | 0%
C 2- Reconstruction / New Service road (Rigid pavement)
|  | (1) Earthwork up to top of the sub-grade | 0%
|  | (2) Sub Base Course | 0%
|  | (3) Dry Lean Concrete (DLC) Course | 0%
|  | (4) Pavement Quality Control (PQC) course | 0%
D - Reconstruction and New culverts on existing road, Realignments, bypasses:
Culverts (Length <6m)
|  | a - Pipe Culverts | 0%
|  | b - Box Culverts | 19.36% |  |  | 100% |  | 78907393
Minor Bridges/ underpasses/ over passes | 33.2% | A 1- Widening and repairs of Minor Bridges (length >6m and <60m) |  | 21.6%
|  | Minor Bridges | 0%
|  | A 2- New Minor Bridges (length >6m and <60m) | [5 empty] | 71292135
|  | (1) Foundation + Sub-structure: on completion of foundation work including foundation for wing and return wall, abutments, piers upto the abutment/pier cap. | 20% |  | 10% |  |  | 49854376 | 69.93% |  | 15748966
|  | (2) Superstructure : on completion of super- structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road sign & markings, tests on completion etc. complete in all respect. |  |  | 0% |  |  |  | 0%
|  |  | 15% |  | 7.5% |  |  | 21142592 | 29.66%
|  | (3) Approaches: on completion of approaches including Retaining walls, stone pitching, protection works complete in all respect, test on completion in all respects and fit for use. |  |  | 0% |  |  |  | 0%
|  |  | 10% |  | 5% |  |  |  | 0%
|  | (4) Guide bunds and river training works: on completion of guide bunds and repair training works complete in all respects. |  |  | 0% |  |  |  | 0%
|  |  | 5% |  | 2.5% |  |  | 295167 | 0.414%
|  | B 1 - Widening and repair of underpasses / overpasses |  |  | 0%
|  | Underpasses / Overpasses | 0% |  | 0%
|  | B 2 - New Underpasses / Overpasses |  |  | 0% |  |  | 60327764
|  | (1) Foundation + Sub-structure: on completion of foundation work including foundation for wing and return wall, abutments, piers upto the abutment/pier cap. | 26.2% |  | 13.1% |  |  | 43673516 | 72.39%
0%
|  | (2) Superstructure : on completion of super- structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road sign & markings, tests on completion etc. complete in all respect. | 13.8% |  | 6.9% |  |  | 16654248 | 27.61%
0%
0%
|  | Wearing coat (a) in case of overpass- wearing coat including expansion joints complete in all respects as specified and | 0% |  | 0%
|  | (b) in case of underpass - rigid pavement including drainage facility complete in all respects as specified. |  |  | 0%
|  | (3) Approaches : On completion of approaches including Retaining walls/ Reinforced earth walls, stone pitching, protection works complete in all respect and fit for use. | 10% |  | 5%
0%
100%
Major bridge (length > 60m) works and RoB / RUB / Elevated sections / Flyovers including viaducts, if any | 2.41% | A 1 - Widening and repair of major bridges |  | 0%
|  | (1) Foundation | 0%
|  | (2) Sub-structure | 0%
|  | (3) Super-structure (including bearings) | 0%
|  | (4) Wearing Coat including expansion joints | 0%
|  | (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0%
|  | (6) Wing walls/return walls | 0%
|  | (7) Guide bunds, River Training works etc. | 0%
|  | (8) Approaches (including Retaining walls, stone pitching and protection works) | 0%
A 2 - New Major bridges
|  | (1) Foundation | 0%
|  | (2) Sub-structure | 0%
|  | (3) Super-structure (including bearings) | 0%
|  | (4) Wearing Coat including expansion joints | 0%
|  | (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0%
|  | (6) Wing walls/return walls upto top | 0%
|  | (7) Guide bunds, River Training works etc. | 0%
|  | (8) Approaches (including Retaining walls, stone pitching and protection works) | 0%
B 1 - Widening and repair of
a) RoB
b) RuB
|  | 1) Foundation | 0%
|  | 2) Sub Structure | 0%
|  | 3) Super Structure (Including bearings) | 0%
4) Wearing coat (a) in case of RoB - wearing coat including expansion joints complete in all respect as specified and (b) in case of RuB - rigid pavement under RuB including drainage facility complete in all respect as specified
0%
|  | 5) miscellaneous items like hand rails, crash barrier, road markings etc | 0%
|  | 6) wing walls / return walls | 0%
|  | 7) Approaches (including Retaining walls, stone pitching and protection works) | 0%
B 2 - New RoB / RuB
a) RoB
|  | b) RuB | [6 empty] | 35773765
|  | 1) Foundation | 25% |  |  |  |  | 20385560 |  | 56.98%
|  | 2) Sub Structure | 25% |  |  |  |  | 11499407 |  | 32.14%
|  | 3) Super Structure (Including bearings) | 25% |  |  |  |  | 3681405 |  | 10.29%
|  | 4) Wearing coat (a) in case of RoB - wearing coat including expansion joints complete in all respect as specified and (b) in case of RuB - rigid pavement under RuB including drainage facility complete in all respect as specified | 15% | [6 empty] | 0%
0%
0%
0%
|  | 5) miscellaneous items like hand rails, crash barrier, road markings etc | 1% |  |  |  |  | 402 |  | 0.001124%
0%
|  | 6) wing walls / return walls | 5% | [6 empty] | 0%
|  | 7) Approaches (including Retaining walls, stone pitching and protection works) | 4% |  |  |  |  | 206991 |  | 0.5786%
C 1 - Widening and repair of Elevated sections / Fly overs / Grade Separators
|  | 1) Foundation | 0%
|  | 2) Sub Structure | 0%
|  | 3) Super Structure (Including bearings) | 0%
|  | 4) Wearing coat including expansion joints | 0%
|  | 5) miscellaneous items like hand rails, crash barrier, road markings etc | 0%
|  | 6) wing walls / return walls | 0%
|  | 7) Approaches (including Retaining walls, stone pitching and protection works) | 0%
C 2 - New Elevated sections / Fly overs / Grade Separators
|  | 1) Foundation | 0%
|  | 2) Sub Structure | 0%
|  | 3) Super Structure (Including bearings) | 0%
|  | 4) Wearing coat including expansion joints | 0%
|  | 5) miscellaneous items like hand rails, crash barrier, road markings etc | 0%
|  | 6) wing walls / return walls | 0%
|  | 7) Approaches (including Retaining walls, stone pitching and protection works) | 0% |  | 100%
Other Works | 4.98% | (i) Toll Plaza | 0% | 13.99%
|  | (ii) Road side drains | [6 empty] | 48111952
|  | Lined Drain | 12.04% |  | 60158976.1558 | 326696293.1558 | 18.41% | 2310 |  | 2310 |  | 46381043 | 96.4% | 12047024.1558 | 60158976.1558
|  | Unlined Drain | 0.78% |  | 1730909 |  | 0.5298% | 7856 |  | 7856 | 10166 | 1730909 | 3.598%
|  | (iii) Road Signs, markings, km stones, safety devices, Road furniture, etc. |  |  |  |  | 0% |  |  |  | 4732.6335
|  |  | 12.8% |  | 38776039 |  | 11.87%
|  | (iv) Project facilities |  |  |  |  | 0%
|  | (a) Bus Bays | 0% |  |  |  | 0%
|  | (b) Truck lay byes | 0% |  |  |  | 0%
|  | © Rest Areas | 0% |  |  |  | 0%
|  | (d) Others |  |  |  |  | 0%
|  | a) Clearing n Grubbing & Dismantling works | 0.43% |  | 1295936 |  | 0.3967%
|  | b) improvement of Junctions | 0% |  |  |  | 0%
|  | c) Sand Filling in embankment in Pond Locations | 0% |  |  |  | 0%
|  | d) Turfing and hydroseeding | 0% |  |  |  | 0%
|  | e) Traffic Aid Post | 0% |  |  |  | 0%
|  | f) Lighting in Built-up areas | 4.1% |  | 11475861 |  | 3.513%
|  | (v) Road side Plantation | 0.5% |  | 1508535 |  | 0.4618%
|  | (vi) Repair of Protection works other than approaches to the bridges, elevated sections / flyovers / grade separators and RoBs/RuBs |  |  |  |  | 0%
|  | (a) Crash Barrier | 0% |  |  |  | 0%
|  | (b) Parapet wall | 0% |  |  |  | 0%
|  | © Retaining wall | 69.35% |  | 213480946 |  | 65.35%
|  | (d) Breast Wall | 0% |  |  |  | 0%
|  | (e) Gabion | 0% |  |  |  | 0%
|  | f) River Training works /Pitching on Slopes | 0%
|  | (vii) Safety and traffic management during construction |  |  | 100%
Internal Infrastructure Works, i.e. Potable Water Supply System including Intake Works, Recycled Water Supply System, Sewerage System | 5.26% | (i) Approval of Hydraulic, Structural Designs, Drawings | 5%
|  | (ii) On supply of all materials, like pipes, valves, etc. at site including transportation, loading, unloading, staking all complete. | 15%
|  | (iii) On completion of all works | 60%
|  | (iv) On satisfactory testing, disinfected of all the system and handling to Employer | 20%
Internal Power Supply System including Street Lighting, Data & Telecommunication | 3.06% | (i) Approval of Designs, Drawings | 5%
|  | (ii) On supply of all materials at site including transportation, loading, unloading, etc. all complete | 20%
|  | (iii) On completion of all works | 65%
|  | (iv) On satisfactory handling over to Employer | 10%
100%
0%

## Sheet3 (hidden)
STAGE FOR PAYMENT | PERCENTAGE WEIGHTAGE | TOTAL CONTRACT PRICE
3 | 4 | 2
A-Widening and Strengthening of existing road
(1) Earthwork up to top of the sub-grade including excavation in soil, soft rock and hard rock, removal of unserviceable soil etc | 3.09%
(2) Sub Base courses | 3.91%
(3) Non Bituminous Base Course | 2.2%
(4) Bituminous Base Course | 4.34%
(5) Wearing coat | 2.5%
(6) Widening and repair of culverts | 0% |  | 16.04%
B 1- New six/ four lane alignment / bypass (Flexible pavement)
(1) Earthwork up to top of the sub-grade | 5.34%
(2) Sub Base Course | 6.43%
(3) Non Bituminous Base Course | 5.62%
(4) Bituminous Base Course | 8.38%
(5) Wearing coat | 6.34% |  | 32.11%
B 2- Reconstruction / New lane alignment / bypass (Rigid pavement)
(1) Earthwork and sub-grade preparation | 12.01% | 0
(2) Sub Base and Base Course | 8.33% | 0
(3) Pavement Courses (DLC and PQC) | 12.15% | 0
(4) Pavement Quality Control (PQC) course | 0% |  | 32.49%
C 1- Reconstruction / New Service road/ Slip Road (Flexible pavement)
(1) Earthwork up to top of the sub-grade | 0%
(2) Sub Base Course | 0%
(3) Non Bituminous Base Course | 0%
(4) Bituminous Base Course | 0%
(5) Wearing coat | 0% |  | 0%
C 2- Reconstruction / New Service road (Rigid pavement)
(1) Earthwork up to top of the sub-grade | 0%
(2) Sub Base Course | 0%
(3) Dry Lean Concrete (DLC) Course | 0%
(4) Pavement Quality Control (PQC) course | 0%
D - Reconstruction and New culverts on existing road, Realignments, bypasses:
Culverts (Length <6m)
a - Pipe Culverts | 0%
b - Box Culverts | 19.36% | 48111952 | 19.36%
| 100% | 48111952

## Road-External
S. No. | Particulars | Amount (In Lacs)
A | EXTERNAL CONNECTIVITY
1 | SITE CLEARANCE & DISMANTLING | 1295936
2 | EARTHWORK & SUBGRADE PREPERATION | 143822134
3 | BASE AND SUB-BASE COURSES | 126643000
4 | PAVEMENT COURSES [FLEXIBLE] | 140291700
5 | Drainage & Protection | 48111952
6 | RE Wall | 213480946
7 | Landscaping | 1508535
8 | Illumination | 11475861
9 | Road Furniture | 38776039
| Cost for Highways | 725406103
10 | Railway Under Bridge | 35773764
11 | Minor Bridge | 71292537
12 | VUP | 60327764
13 | Culvert | 78907393
| Cost for Structures | 246301458
971707561

## Road-Internal
Road Items
Sl no | MORTH Ref | Description | Unit | Qty | Rate | Amount
1 | Section-201 | Clearing and grubbing site are/ road land including uprooting rank vegetation, grass, bushes, shrubs, saplings and trees girth up to 300 mm, removal of stumps of trees cut earlier and disposal of unserviceable materials and stacking of serviceable material to be used or auctioned, up to a lead of 1000 metres including removal and disposal of top organic soil not exceeding 150 mm in thickness | Hec | 10 | 40291 | 402910
2 | Section-301 | Excavation for roadwork in soil with hydraulic excavator of 0.9 cum bucket capacity including cutting and loading in tippers, trimming bottom and side slopes, in accordance with requirements of lines, grades and cross sections, and transporting to the embankment location within all lifts and lead upto 1000m | Cum | 57642 | 84 | 4841948.58
3 | Section-305 | Construction of subgrade and earthen shoulder satisfying the requirements of minimum soaked CBR value as indicated in the drawings with approved borrow area material,with all leads and lifts ,all includings asper drawings and MORTH specifiation | Cum | 35600 | 290 | 10324000
4 | Section-305 | Construction of embankment with suitable material obtained from roadway, drainage excavation etc. with all leads and lifts all complete as per drawings and Technical Specification Clause 305. | Cum |  | 103 | 0
5 | Section-305 | Construction of embankment with approved material obtained from borrow pits with all lifts and leads, transporting to site, spreading, grading to required slope and compacting to meet requirement of table 300-2. | Cum | 243908 | 238 | 58050215.86
6 | Section-401 | Providing, laying, spreading and compacting graded stone aggregate to granular sub base as per specification including premixing the Material with water at OMC in mechanical mix plant carriage of mixed Material by tipper to site, laying in uniform layers with paver in sub- base course on well prepared surface and compacting with vibratory roller to achieve the desired density. | Cum | 17400 | 2033 | 35374200
7 | Section-408 | Construction of median and Island above road level with approved material deposited at site from roadway cutting andexcavation for drain and foundation of other structures, spread, sloped and compacted as per clause 408 | Cum | 2500 | 264 | 660000
8 | Section-601 | Dry Lean Cemenht Concrete Sub-base(Construction of dry lean cement concrete Sub-base over a prepared sub-grade with coarse and fine aggregate conforming to IS:383,the size of coarse aggregate not exceeding 25mm,aggregate cement ratio not to exceed 15:1,aggregate gradation after blending to be determined during trial length construction, concrete strength not to be less than 10 Mpa at 7 days,mixed in a batching plant, transported to site, laid with a paver with electronic sensor, compacting with 8-10 tonnes vibratory roller, finishing and curing | Cum | 9200 | 3952 | 36358400
9 | Section-602 | Cement Concrete Pavement (Construction of un-reinforced,dowel jointed, plain cement concrete pavement over prepared sub base with 43 grade cement @400mkg per cum, coarse and fine aggregate conforming to IS 383, maximum size of coarse aggregate not exceeding 25 mm, mixed in a batching and mixing plant as per approved mix design, transported to site, laid with a fixed form or slip form paver,spread, compacted and finished in a continuous operation including provision of contraction, expansion ,construction and longitudinal joints, joint filter, seperation membrane, sealant primer, joint sealant, debonding strip, dowel bar, tie rod, admixtures as approved, curing compound, finishing to lines and graded as per drawing) | Cum | 17100 | 8306 | 142032600
10 | Section-409 | Construction of cement concrete kerb with channel with top and bottom width 115 and 165 mm respectively, 250 mm high in M 20 grade PCC on M15 grade foundation 150 mm thick, kerb channel 300 mm wide, 165 mm thick in PCCM20 grade, sloped towards the kerb, kerb stone with channel laid with kerb laying machine, foundation concrete laid manually, all complete as per clause 409 | Rm | 9000 | 660 | 5940000
11 | Section-409 | Cast in Situ Cement Concrete M20 Kerb Construction of cement concrete kerb with top and bottom width 115 and 165 mmrespectively, 250 mm high in M 20 grade PCC on M-10 grade foundation 150 mmthick, foundation having 50 mm projection beyond kerb stone, kerb stone laid withkerb laying machine, foundation concrete laid manually, all complete as per clause409 | Rm | 18300 | 350 | 6405000
12 | Section-803 | Providing and laying of hot applied thermoplastic compound 2.5 mm thick including sq.mreflectorising glass beads @ 250 gms per sqm area, thickness of 2.5 mm is exclusiveof surface applied glass beads as per IRC:35 .The finished surface to be level,uniform and free from streaks and holes.
|  | Edge Lines and Centre Lines | Sqm | 1231.73 | 876 | 1078996.41
|  | Pedestrian Crossing Marking | Sqm | 315 | 876 | 275940
|  | Chevron Marking | Sqm | 210 | 876 | 183960
|  | Stop line | Sqm | 42 | 876 | 36792
|  | Arrow | Sqm | 300 | 876 | 262800
13 | Section-801 | Providing and fixing of retro-reflectorised cautionary, mandatory and informatorysign as per IRC:67 made of encapsulated lens type reflective sheeting vide Clause1701.2.3, fixed over aluminium sheeting, 1.5 mm thick supported on RCC Post 100mm x 100 mm firmly fixed to the ground by means of properly designed foundationwith M15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm belowground level as per approved drawing Clause 1701
|  | (i) Octagonal Boards - ( 900 mm Octagonal ) | No | 28 | 9515 | 266420
|  | (ii) Triangular Boards - ( 900 mm Equilateral Triangles) | No | 100 | 6106 | 610600
|  | (iii) Circular Boards - ( 600mm /900mm Circular) | No | 30 | 5397 | 161910
|  | (iv) Rectangular Boards -( Size 300mmx900mm) | No | 46 | 5259 | 241914
|  | (v) Rectangular Boards -( Size 600mmx800mm) | No | 6 | 7483 | 44898
|  | (vi) Direction and Place Identification Signs upto 0.9 sqm Size Board. ( Cantilever Type) | No | 14 | 13243 | 185402
|  | (vii) Overhead Gantrie. (Full width) | No | 1 | 250000 | 250000
|  | (viii) Single chevron Boards -( Size 600mmx500mm) | No | 20 | 6212 | 124240
14 |  | Paver Block on footpath and Cycle track (60mm thick) (ICBP) | Sqm | 33200 | 805 | 26726000
15 |  | Sand Filling below footpath (50 mm thick) | Cum | 1700 | 1448 | 2461600
|  |  | Total |  |  | 333300747
|  | Arrow | Sqm |  | 876 | 262800
13 | Section-801 | Providing and fixing of retro-reflectorised cautionary, mandatory and informatorysign as per IRC:67 made of encapsulated lens type reflective sheeting vide Clause1701.2.3, fixed over aluminium sheeting, 1.5 mm thick supported on RCC Post 100mm x 100 mm firmly fixed to the ground by means of properly designed foundationwith M15 grade cement concrete 450 mm x 450 mm x 600 mm, 600 mm belowground level as per approved drawing Clause 1701
|  | (i) Octagonal Boards - ( 900 mm Octagonal ) | No |  | 9515 | 266420
|  | (ii) Triangular Boards - ( 900 mm Equilateral Triangles) | No |  | 6106 | 610600
|  | (iii) Circular Boards - ( 600mm /900mm Circular) | No |  | 5397 | 161910
|  | (iv) Rectangular Boards -( Size 300mmx900mm) | No |  | 5259 | 241914
|  | (v) Rectangular Boards -( Size 600mmx800mm) | No |  | 7483 | 44898
|  | (vi) Direction and Place Identification Signs upto 0.9 sqm Size Board. ( Cantilever Type) | No |  | 13243 | 185402
|  | (vii) Overhead Gantrie. (Full width) | No |  | 250000 | 250000
|  | (viii) Single chevron Boards -( Size 600mmx500mm) | No |  | 6212 | 124240
14 |  | Paver Block on footpath and Cycle track (60mm thick) (ICBP) | Sqm |  | 805 | 26726000
15 |  | Sand Filling below footpath (50 mm thick) | Cum |  | 1448 | 2461600
|  |  | Total |  |  | 333300746.8544

## Sheet2 (hidden)
| Bill description | Unit | Qty. | Rate | Amount
Drainage and protection
1 | Surface Drains in Soil (Construction of unlined surface drains of average cross sectional area 0.40 sqm in soil to specified lines, grades, levels and dimensions to the requirement of clause 301 and 309. | Rm | 8686 | 81 | 703566 | 1730909
| Excavation | Cum | 3465 | 84 | 291060
| Providing foundation of drains in PCC M15 | Cum | 393 | 5644 | 2218092
| Providing RCC M20 in road side drains including centering & shuttering but excluding reinforcement | Cum | 2125 | 345 | 733125
| Supplying, Fitting and Placing un-coated HYSD bar Reinforcement complete as per Drawing and Technical Specifications. | MT | 96 | 78391 | 7525536
| Weep Holes | Nos. | 2310 | 199 | 459690
| Vertical Grating | Nos. | 116 |  | 0
| Embankment protection with Turfing | Sqm | 22760 | 31 | 705560
12636629
48111952
35475323

## PWS
PROPOSED EXTERNAL WATER SUPPLY SYSTEM
ABSTRACT ESTIMATE
S.No | Components | Amount (Rs.)
A | Pumping Main Arrangements:
1 | Construction of Intake Well at Brahmaputra River near to MMLP | 5000000
2 | Supply,Delivery and Erection of Vertical Turbine Pump sets from Intake to Raw water Sump | 1227042
3 | Providing 250 DI Class K-9 Pumping Main from Intake to Raw Water Sump near WTP including valves, valve chambers etc. complete. | 26722659.09
4 | Construction of 150 KLD Raw Water Sump at WTP | 2457137
5 | Supply,Delivery and Erection of Submersible Pump sets from Raw water Sump to WTP | 374929.5
6 | Construction of 2.00 MLD Capacity Rapid Gravity Filtration Plant including civil, mechanical and electrical fully automation including trial running etc., complete | 10582000
| Sub Total - A | 46363767.59
B | GST & Other L.S provisions
7 | Provision towards Works Contract GST @ 12% | 5563652
8 | Unforeseen items | 3072580.41
| Sub Total - B | 8636232.41
| Grand Total (A+B) | 55000000
| Grand Total in Lakhs | 550
Potable Water Supply Network :-
1 | Construction of 100 KL Clear Water Sump at WTP | 2343168
2 | Supply, Delivery and Erection of Submersible Pump sets from Sump to OHSR | 448591.5
3 | Providing HDPE PN 6 Gravity mains from Sump to blocks including valves, valve chambers etc. complete. | 4952447
| Sub Total - B | 7744206.5
| Total (A+B) | 57180554.5

## RWS
PROPOSED RECYCLED WATER SYSTEM
ABSTRACT ESTIMATE
S.No | Components | Amount (Rs.)
A | Recycle Water Network :-
1 | Supply, Delivery and Erection of Submersible Pump sets from Sump to Plots (MMLP) | 320422.5
2 | Construction of 50 KL Recycled Water Sump at STP | 2202309
3 | Providing HDPE PN-10 Pumping mains from Sump to Plots (MMLP) including valves, valve chambers etc. complete. | 4371704
| Sub Total - A | 6894435.5
B | GST & Other L.S provisions
4 | Provision towards Works Contract GST @ 12% | 827332
5 | Unforeseen items | 278232.5
| Sub Total - B | 1105564.5
| Grand Total (A+B) | 8000000
| Grand Total in Lakhs | 80

## SWD
S.No | Components | Amount (Rs.)
A | Storm Water Draianage
1 | Construction of Storm water drains for MMLP | 63484427
| Sub Total - A | 63484427
B | GST & Other L.S Provisions
2 | Provision towards Works Contract GST @ 12 % | 7618131
3 | Unforeseen items | 2897442
| Sub Total - B | 10515573
| Grand Total (A+B) | 74000000
| Grand Total in Lakhs | 740

## SEW
S. No | Description | Amount (Rs.)
A | Cost of Sewerage Network of length as per the design
1 | Sewerage Network Length 3.4 km, including STP to Outfall to disposal location, Manholes, Inspection Chambers, House Service Connections. | 53712562.91
Man holes-136Nos
HSCs-63Nos
Ics-31.5Nos
2 | Providing 0.5 MLD STP incuding Operation and Maintanance | 14255000
| Sub Total A | 67967562.91
B | LS Provisions
3 | Provision towards Mechanical sewer cleaning equipments | 805688.44
| Sub Total B | 805688.44
| Sub Total A + Sub Total B | 68773251.35
C | Other LS Provisions
4 | Provision towards U/F items of works etc,. | 1470641.1
5 | Provision towards GST @ 12% | 8156107.55
| Sub Total C | 9626748.65
| GRAND TOTAL | 78400000
| Grand Total in Lakhs | 784

## ED
S. No. | Particulars | Amount (In Lacs)
A | EXTERNAL INFRUSTRUCTURE DEVELOPMENT WORKS
4 | 33kV Under Ground Network | 3932924.029
5 | 11kV Under Ground Network | 8441015.5147
6 | Street lighting | 19147707.97
7 | Telecommunications/ Data Network Conduiting | 279190.9091
8 | ( D.G SET WORKS )
9 | ( ELV WORKS )
10 | SOLAR WORKS | 15084500
46885338.4227